## Team 5 - Project Plan
COLOUR |  | Completed |  |  |  | SPRING 2022 SEMESTER
Incomplete
Team Members | Aleksander , Christus, Yash , Preethi , Pratikkumar, Yashraj |  |  |  | Week# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[5 empty] | Date | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
Project phase | Activity | Task owner | Start date | End date | Progess %
Project Initiation and Planning | Discuss project proposals | ALL | 2022-01-25 | 2022-01-25 | 100
| Confirm Project Team Roles | Prof and ALL | 2022-01-26 | 2022-02-01 | 100
| Develop two business cases | Team-1(Yash, Aleksander, Christus) | 2022-01-27 | 2022-02-08 | 100
|  | Team-2(Preethi,Pratikkumar,Yashraj) | 2022-01-27 | 2022-02-08 | 100
| Develop Project Initiation Document (PID) | ALL | 2022-02-08 | 2022-02-12 | 100
| Produce initial Project Plan, RACI | Project Plan(Yash,Yashraj) | 2022-02-15 | 2022-02-18 | 80
|  | RACI(Pratikkumar,Aleksander) | 2022-02-18 | 2022-02-22 | 100
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Analysis | Produce BRM diagram, define User Roles | Aleksander, Christus | 2022-02-22 | 2022-03-01
| Produce Context Diagram, Define System Interfaces | Yash, Yashraj | 2022-02-22 | 2022-03-01
| Team discussion of Requirements Types | ALL | 2022-02-22 | 2022-03-01
| Agree to customer needs | Pratikkumar, Preethi | 2022-02-22 | 2022-03-01
| Define Functional Decomposition | Y | 2022-03-01 | 2022-03-07
| Produce RCT document | Y | 2022-03-01 | 2022-03-07
| Home pkge menu design | A | 2022-03-01 | 2022-03-07
| Produce analysis diagrams (UML, DFD) | ALL | 2022-03-01 | 2022-03-07
| Define functional requirements (User Stories) | ALL | 2022-03-08 | 2022-03-14
| Update Project Plan with additional requirements tasks | ALL | 2022-03-08 | 2022-03-14
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | CM/A | 2022-03-15 | 2022-03-21
| Database Design (ERD, Table spec) | CM | 2022-03-15 | 2022-03-21
| System Interface Design | A | 2022-03-22 | 2022-03-29
| User interface design | PK/A | 2022-03-22 | 2022-03-29
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | A | 2022-03-29 | 2022-04-05
| Establish code repository in GitHUb | A | 2022-03-29 | 2022-04-05
| Coding & Implemenation | A | 2022-03-29 | 2022-04-05
MILESTONE 4: CODING COMPLETED
Integration &testing | Plan testing, produce a Test Plan document | P | 2022-04-06 | 2022-04-12
| Evaluate Features to be Tested | P | 2022-04-06 | 2022-04-12
| Design Test Cases | P | 2022-04-12 | 2022-04-19
| Execute Test Cases | P | 2022-04-19 | 2022-04-26
| Testing workshop + Application demo | ALL | 2022-04-19 | 2022-04-26
MILESTONE 5: TESTING COMPLETED
Final Exam | Final Exam | ALL | 2022-05-03
Presentation | Prepkre Application Demo for the Presentation | ALL | 2022-05-10 | 2022-05-10