## Team 5 - Project Plan
COLOUR |  |  | Completed |  |  |  | SPRING 2022 SEMESTER
Incomplete
Team Members | Aleksander , Christus, Yash , Preethi , Pratikkumar, Yashraj |  |  |  |  | Week# | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | Date | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10
Project phase | Activity |  | Task owner | Start date | End date | Progess %
Project Initiation and Planning | Discuss project proposals |  | ALL | 2022-01-25 | 2022-01-25 | 100
| Confirm Project Team Roles |  | Prof and ALL | 2022-01-26 | 2022-02-01 | 100
| Develop two business cases |  | Team-1(Yash, Aleksander, Christus) | 2022-01-27 | 2022-02-08 | 100
|  |  | Team-2(Preethi,Pratikkumar,Yashraj) | 2022-01-27 | 2022-02-08 | 100
| Develop Project Initiation Document (PID) |  | ALL | 2022-02-08 | 2022-02-12 | 100
| Produce initial Project Plan |  | Project Plan(Yash,Yashraj) | 2022-02-15 | 2022-02-18 | 80
| RACI |  | RACI(Pratikkumar,Aleksander) | 2022-02-18 | 2022-02-22 | 100
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Analysis | Produce BRM diagram, define User Roles |  | Aleksander, Christus | 2022-02-22 | 2022-03-01 | 100
| Produce Context Diagram, Define System Interfaces |  | Yash, Yashraj | 2022-02-22 | 2022-03-01 | 100
| Team discussion of Requirements Types |  | ALL | 2022-02-22 | 2022-03-01 | 100
| Agree to customer needs |  | Pratikkumar, Preethi | 2022-02-22 | 2022-03-01 | 100
| Business Requirements |  | ALL | 2022-03-01 | 2022-03-07 | 100
| Define Functional Decomposition |  | Pratikkumar, Yashraj | 2022-03-01 | 2022-03-07 | 100
| Produce RCT document |  | Yash, Yashraj, Aleksander, Christus | 2022-03-01 | 2022-03-07 | 100
| Home page menu design |  | Aleksander | 2022-03-01 | 2022-03-07 | 100
| Produce analysis diagrams (UML, DFD, ACT DIAG) |  | ALL | 2022-03-08 | 2022-03-21 | 100
| Define functional requirements (User Stories) |  | Yash, Preethi | 2022-03-08 | 2022-03-21 | 100
| Update Project Plan with additional requirements tasks |  | Yash | 2022-03-08 | 2022-03-21 | 100
Mid-term Exam | Mid-term Exam |  | ALL | 2022-03-22 | 2022-03-29 | 100
MILESTONE 2: REQUIREMENTS COMPLETED
Design | ER Diagrams (conceptual -> logical) |  | Christus, Yashraj | 2022-03-30 | 2022-04-05 | 100
| Database Table Specs |  | ALL | 2022-03-30 | 2022-04-05 | 100
| Test Database Table specs |  | Yash | 2022-03-30 | 2022-04-05 | 100
| Data-flow Diagram (physical) |  | Aleksander | 2022-03-30 | 2022-04-05 | 100
| Architectural Logical Design |  | Aleksander, Yash, Yashraj | 2022-04-06 | 2022-04-12 | 100
| Architectural Process Design |  | Christus, Pratik, Preethi | 2022-04-06 | 2022-04-12 | 100
| Establish GitHub Project |  | Aleksander | 2022-04-06 | 2022-04-12 | 100
| Class Diagram (UML) |  | Yashraj, Yash | 2022-04-13 | 2022-04-19 | 100
| Sequence Diagram (UML) |  | Pratik, Preethi | 2022-04-13 | 2022-04-19 | 100
| Populate test data in the database tables |  | Christus | 2022-04-13 | 2022-04-19 | 100
MILESTONE 3: DESIGN COMPLETED
Code | Manage Account | 1.01 Register User | Aleksander, Yash | 2022-04-13 | 2022-04-19 | 100
|  | 1.03 Account Authentication | Aleksander, Yash | 2022-04-13 | 2022-04-19 | 100
| Donate & Receive | 2.01 List Food items for donation | Aleksander, Yash | 2022-04-13 | 2022-04-19 | 100
|  | 2.02 Provide package information | Aleksander, Yash | 2022-04-13 | 2022-04-19 | 100
|  | 2.03 Provide Pickup time & location | Aleksander, Yash | 2022-04-13 | 2022-04-19 | 100
| Create and manage Server |  | Aleksander | 2022-04-13 | 2022-04-19 | 100
| Source code in GitHub repository, executable code ready for testing |  | Aleksander | 2022-04-13 | 2022-04-19 | 100
MILESTONE 4: CODING COMPLETED
Integration &testing | Test Plan Document |  | Christus, Yashraj | 2022-04-20 | 2022-04-26 | 100
| Design Test Specifications - 1.01 Register User |  | Yash | 2022-04-20 | 2022-04-26 | 100
| Design Test Specifications - 1.03 Account Authentication |  | Pratik, Preethi | 2022-04-20 | 2022-04-26 | 100
| Execute Test Specifications - 1.01 Register User |  | Christus | 2022-04-20 | 2022-04-26 | 100
| Execute Test Specifications - 1.03 Account Authentication |  | Yashraj | 2022-04-20 | 2022-04-26 | 100
| Testing workshop + Application demo |  | ALL | 2022-04-20 | 2022-04-26 | 100
MILESTONE 5: TESTING COMPLETED
Final Exam | Final Exam |  | ALL | 2022-05-03 | 2022-05-03 | 100
Presentation | Prepare Application Demo for the Presentation |  | ALL | 2022-05-10 | 2022-05-10 | 100